## ISO27001_Controls
Control ID | Requirement | Current Status | Control Owner | Action Needed | Maturity Level | Target Date | Risk Context | Dependencies | Priority
A.5.15 | Access Control | Planned | IT Manager | Develop and implement an access control policy for all systems | Initial | 2026-02-05 | Risk: Unauthorized access → Data breach and compliance violation | Source Code Access (A.8.4) | High
A.5.16 | Identity Management | Planned | IT Manager | Implement identity lifecycle management (provisioning, de-provisioning, periodic reviews) | Initial | 2026-02-13 | Risk: Orphaned accounts → Data breach and compliance violation | Access Control (A.5.15) | High
A.5.23 | Information security for use of cloud services | Planned | AI Officer / Operations Lead | Create and enforce a cloud usage policy covering AWS and SaaS tools | Initial | 2026-02-15 | Risk: Misconfigured SaaS → Data exposure and compliance violation | Configuration Management (A.8.9) | High
A.5.34 | Privacy and protection of PII | Planned | Data Protection Officer | Develop and implement a data privacy policy aligned with ISO 27001 | Initial | 2026-02-03 | Risk: Unprotected PII → regulatory fines and reputational damage | Information deletion (A.8.10) and Data Masking (A.8.11) | High
A.6.1 | Screening | Planned | HR Manager | Conduct background checks for new hires | Initial | 2026-02-28 | Risk: Insider threat → organizational and reputational damage |  | High
A.6.3 | Information security awareness, education and training | Planned | Security Officer | Develop and deliver annual security awareness training for all staff | Initial | 2026-03-15 | Risk: Social engineering → Data breach, financial harm, compliance violation |  | Medium
A.6.6 | Confidentiality or non-disclosure agreements | Planned | Legal Officer | Ensure all employees sign confidentiality agreements | Initial | 2026-02-25 | Risk: Insider threat → loss of competitive edge and organizational damage |  | High
A.6.7 | Remote working | Partially Implemented | IT Manager | Audit remote work security controls (VPN, MFA, endpoint protection) | Developing | 2026-02-18 | Risk: Unauthorized access → Data breach and compliance violation |  | High
A.7.9 | Security of assets off-premises | Partially Implemented | IT Manager | Audit security of laptops and mobile devices used remotely | Developing | 2026-02-23 | Risk: Unauthorized access → Data breach and compliance violation |  | High
A.8.1 | User endpoint devices | Partially Implemented | IT Manager | Deploy EDR and enable logging on all laptops | Developing | 2026-02-03 | Risk: Malware infection → Service disruption and data compromise |  | High
A.8.4 | Access to source code | Partially Implemented | AI Officer | Restrict source code access based on least privilege and audit permissions | Developing | 2026-02-05 | Risk: Unauthorized access → Data breach and compliance violation |  | High
A.8.9 | Configuration management | Partially Implemented | Chief Technical Officer / IT Manager | Document and enforce configuration baselines for servers and SaaS tools | Developing | 2026-02-08 | Risk: Misconfigurations → Unauthorized access or downtime |  | High
A.8.10 | Information deletion | Planned | AI Officer / Chief Technical Officer | Implement secure deletion processes for ML datasets and customer data in cloud storage | Initial | 2026-02-28 | Risk: Unprotected PII → regulatory fines and reputational damage |  | High
A.8.11 | Data masking | Partially Implemented | IT Manager | Apply data masking for PII in development and testing environments | Developing | 2026-03-18 | Risk: Unprotected PII → regulatory fines and reputational damage |  | Medium
A.8.22 | Segregation of networks | Partially Implemented | Chief Technical Officer | Implement network segmentation for production, staging, and admin environments | Developing | 2026-03-30 | Risk: Unauthorized access → Data breach and compliance violation |  | Medium
See Legend tab for definitions of Current Status and Control Owner.

## Asset_Register
Asset ID | Asset Name | Type | Asset Owner (Accountable) | Custodian (Technical) | Location | Classification | Criticality | Responsible Control | Backup Status | Encryption Status | Patch Status | Notes
LAP-001 | Employee Laptop (Serial: ABC) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-002 | Employee Laptop (Serial: DEF) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-003 | Employee Laptop (Serial: GHI) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-004 | Employee Laptop (Serial: JKL) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-005 | Employee Laptop (Serial: MNO) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-006 | Employee Laptop (Serial: PQR) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-007 | Employee Laptop (Serial: STU) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
LAP-008 | Employee Laptop (Serial: VWX) | Hardware | IT Manager | Employee | Remote | Confidential | Medium | A.8.1 | No | Yes | No | Patch management pending for laptops
NET-GWY-001 | Office Network Infrastructure (Router & Firewall) | Hardware | IT Manager | System Administrator | Office | Restricted | High | A.8.22 | Yes | Yes | Yes
SRV-001 | Cloud Production Server (AWS EC2) | Server | IT Manager | Cloud Architect | Cloud | Restricted | High | A.5.23 | Yes | Yes | Yes | Assumed AWS default encryption enabled
SRV-002 | Staging/Test Server | Server | IT Manager | DevOps Lead | Cloud | Restricted | Medium | A.8.10 | Yes | Yes | Yes
SRV-003 | GPU Compute Instance (AWS EC2 with NVIDIA GPUs for ML training) | Server | AI Officer | Cloud Architect | Cloud | Restricted | High | A.5.15 | Yes | Yes | Yes | Assumed AWS default encryption enabled
DAT-001 | ML Model Storage (AWS S3 bucket) | Data Storage | AI Officer | Cloud Architect | Cloud | Confidential | High | A.8.10 | Yes | Yes | N/A | Patching not applicable to storage
DAT-002 | Customer Data Storage (secure cloud storage) | Data Storage | IT Manager | Data Protection Officer | Cloud | Confidential | High | A.5.34 | Yes | Yes | N/A | Patching not applicable to storage
SFT-SAAS-001 | GitHub (code repository) | SaaS Tool | IT Manager | DevOps Lead | Cloud | Restricted | High | A.8.4 | Yes | Yes | Yes | Vendor-managed patching and encryption
SFT-SAAS-002 | Slack (communication) | SaaS Tool | HR Manager | System Administrator | Cloud | Internal | Medium | A.8.9 | Yes | Yes | Yes | Vendor-managed patching and encryption
SFT-SAAS-003 | Google Workspace (email, docs) | SaaS Tool | IT Manager | System Administrator | Cloud | Confidential | High | A.8.9 | Yes | Yes | Yes | Vendor-managed patching and encryption
SFT-SAAS-004 | Jira (project management) | SaaS Tool | IT Manager | IT Manager | Cloud | Internal | Medium | A.8.9 | Yes | Yes | Yes | Vendor-managed patching and encryption
SFT-SAAS-005 | AWS (cloud infrastructure) | SaaS Tool | IT Manager | Cloud Architect | Cloud | Restricted | High | A.8.9 | Yes | Yes | Yes | Vendor-managed patching and encryption
SFT-EPP-001 | Endpoint Protection (CrowdStrike) | Security Tool | Security Officer | System Administrator | Cloud | Restricted | High | A.6.7 | N/A | Yes | Yes | Vendor-managed patching
SFT-VPN-001 | VPN Service for Remote Access | Security Tool | Security Officer | System Administrator | Cloud | Restricted | High | A.6.7 | N/A | Yes | Yes | Vendor-managed patching
See Legend tab for definitions of Asset Owner, Custodian, Classification, and Criticality.

## Legend
Term | Definition
Current Status | Control implementation: Planned, Partially Implemented, Implemented.
Planned | Control has been identified but not yet implemented.
Partially Implemented | Control is in progress; some measures are in place but not complete.
Implemented | Control is fully in place and operational.
Control Owner | Role accountable for implementing and maintaining the ISO 27001 control.
Asset Owner | Role accountable for compliance and governance of the asset.
Custodian | Technical role responsible for managing and maintaining the asset.
Classification | Sensitivity level: Confidential, Restricted, Internal.
Confidential | Customer data or proprietary information.
Restricted | Critical infrastructure or security tools.
Internal | General business tools, not highly sensitive.
Criticality | Business impact: High, Medium, Low.
High | Essential for business continuity.
Medium | Important but not mission-critical.
Low | Minimal impact if unavailable.